## Review
OpenETCS Review Sheet

Work Package	WP4
Deliverable ID	D4.2.3

Document title	openETCS Hazard and Risk Analysis Methodology
Document version	00.20
Document author(s)	Jan Welte
Organisation	TU-BS
Document approbation

Review opening date	19.03.2014
Review closing date	16.04.2014

Reviewer's name	Organisation	Initials		Explanations:
Olivier Hervillard	Systerel	OH		Review: main sheet providing the document and review information.
Stephan Jagusch	Aebt	SJ		Comments: detailed comments and the answer provided
Hardi Hunger	DLR	HH		Main Issues: main/open issues on the document after review
Marielle Petit-Doche	Systerel	MPD
Abdelnasir Mohamed	Aebt	AM

## Comments
Comments

#	Reviewer	Page/§/Req.	Maj/Min/Q	Comment	Answer	OK/NOK/OPEN
	OH	Refer to chapters 1 and 5. OpenETCS Safety Case of openETCS Hazard and Risk Analysis Methodology		The document indicates that the plan of safety case will be developed. In section 5, it is not the whole plan that is shown but rather the three kind of evidence in compliance to the safety acceptance conditions (§5.1 of EN50129)	Chapter 1 has been changed to state more clearly, that this document only presents a methodology to do the safety plan. This document is not the safety plan and, respectively, can not show the whole plan.	OK
	OH			As explained in section 3.39 of EN 50126 standard , planning and responsibilities of technical documents must be defined in the safety plan (Refer to comment 3).	As this document is not the full safety plan itself, this points can not be addressed at the current state. They will be handled as far as possible in the future work.	Ok
	OH	Refer to 3.OpenETCS Development process of openETCS Hazard and Risk Analysis Methodology		It could be interesting to include FDMS activies in the table 1 " Phases openETCS software development process", for each phase. Add coloumns (FMDS Activities, Responsaiblity, document reference) or create new table.	This is a good aspect, which is definitly needed to describe the development process. As this document shall only give a short overview of the process, such a table would probably give to much detailed information at this point. Therefore this point shall be considered in the follow up word to detail the development plan.	Open
	OH	Refer to 1.2 Document Structure (page 2) :		The basic open ETCS software develpment (development)	corrected	OK
	OH	Refer to 3.1 Formalization and software development (page 9) :		Corresponding to the development artifacts the openETCS development process has 5 main distinguishable phase (phases)	corrected	OK
	OH	Refert to 5.1 Structure (page 16) :		Overall the openETCS will separate between the following three kind of evidence (evidences)	evidence has no plural in english	NOK
	OH	§1		EN50128 defines safety versus human harming only not versus environment (3.1.27 of EN50128-2011)	Definition is given in subsection 1.6.4 (the more general definition defining safety as risk of harm for the enviroment is not part of the EN 50128 to limit the liability)	Ok
	SJ	Chapter strucure:		-The Safety plan should reference to each phase (subchapter) of the System and Software Lifecycle.	As this document is not the full safety plan itself, this points can not be addressed at the current state. They will be handled as far as possible in the future work.	NOK
	SJ	Chapter strucure:		-It should be defined, what documents are necessary as input for a phase	Will be address in the upcoming work	NOK
	SJ	Chapter strucure:		-It should be defined, what documents has to be done in the phase	Will be address in the upcoming work	Ok
	SJ	Chapter strucure:		-It should be defined, what documents are to be created in the phase	Will be address in the upcoming work	Ok
	SJ	Chapter strucure:		-It should be defined, what exit criteria have to be met, in order to complete a phase (Review, Test etc..)	Can not be specified here as this has to be defined in detail based on the concrete steps	Open
	SJ	Described Lifecycle:		-The stated lifecycle is ambigues. Its not clearly divided what is System and what is Software development	Changed text in section formalization and software development to emphasis that openETCs only does software development and just processes input from the overall ETCS system development	OK
	SJ	Described Lifecycle:		-It "seems" to be compliant to the SW Lifecycle (EN50128 - Figure 4), but Reference to the Standards are missing	Added number of direct references to the standard, but this will mainly be done in the detailed description of the process	Ok
	SJ	Overall Lifecycle:		-An overall Lifecycle should be defined (System development)	Only a Software lyfecycle is context of openETCS. This has to be defined in the Development documents	Open
	SJ	Overall Lifecycle:		-The Overall lifecycle should have an interface to the Software-Lifecycle (usually Apportionment of System Requirements)	Here the appointment of Subset 26 and other requirements to the software is the interface to the overall life cycle. Text and figure 7 has been modified to address this point.	Ok
	SJ	Overall Lifecycle:		-The overall Lifecycle should have references to the standards (EN50126/50129)	Only a Software lyfecycle is context of openETCS. This has to be defined in the Development documents	Open
	HH	Document title:		Hazard and Risk Analysis and Safety Case	Changed titel to "openETCS Hazard and Risk Analysis and Safety Case Methodology" (but I'm still not satisfied with the titel)	OK
	HH			Several details concerning spelling and English grammar - not listed here	Addressed as far as possible	Ok
	HH			Doc Control - ID and title tbc.	Document ID changed to D 4.2.3 and doc control updated with review data	OK
	HH	Abstract:		Should state both aspects: HRA and SC, Plan for the HRA and summary of performed activities. SC currently plan, future version also openETCS SC (which is partly generic)	Abstracted changed to incorporate HRA and SC.	OK
	HH	1.1 Purpose:		Still refers to "safety plan".	Term safety plan eliminated	OK
	HH	1.1 Purpose:		I would see the purpose of the document (see also above) / 1. plan and report on the hazard and risk analysis, and / 2. to prepare the contribution to the safety case / - of the openETCS development / - for a complete EVC which uses the openETCS software	Purpose has been rewriten to mainly reflect these points	OK
	HH	3 openETCS Development Process		3.1 is the best description of the openETCS SW development process I have seen so far. Should be moved to a separate document(Proposal: openETCS [SW] Development Plan) or to the QA plan. Then this description can be referenced by other documents (this one, the V&V plan, etc). Needs to be maintained, too.	Activities started by Hardi Hunger to collect the development process information in central location to be referenced and updated - as this work is ongoing the section is left in place	Open
	HH	3 openETCS Development Process		3.2 is largely ok	comments concerning specific issues in 3.2 have been integrated	OK
		3 openETCS Development Process		3.2.3 Validation cannot ensure the overall safety requirements. It is only one step of the assurance activities (and can usually not contribute much to safety assurance).	I've eliminated the term overall safety requirements as this term is too ambiguous. However, I would like do have a discussion about the second part of your comment, as I've the feeling we have a different understanding what is meant with safety requirements validation.	OK
	HH			4. Hazard and Risk Analysis / More structure to the section would be desirable. Proposal following.	I've to agree	OK
	HH			4.1 Definition of HRA (short standard summary, could also be done in "Background material"))	Detailed presentation of the hazard and risk analysis requirements for system development and the resulting risk reduction process has been added to the "background material"	OK
	HH			4.1.2 Purpose: To provide detailed information on dangers which arise from the system/software in its operational, to be able to control the dangers and achieve to limit the risk to an acceptable level.		OK
	HH			4.1.2 Scope: Start at system level, refine at need at more detailed development stages.		OK
	HH			4.1.3 Objectives: / At system level: / a) to d) from EN 50126 (hazard identification, events for hazards, determine risks, design risk management process) / At a later stage: / - refine the hazard description / - recompute the risk / (i.e. perform the risk management as defined in d) above)		OK
	HH			4.1.4 Activities: / Define the activities and the methods to be applied (select from 50126)		OK
	HH			4.2 Plan HRA for openETCS		OK
	HH			4.2.1 Purpose: Instantiation of 50126 process for openETCS		OK
	HH			4.2.2 Scope / - System and Specification / (Object of initial step of HRA, relevant specs) / - identify later stages (as far as foreseeable)		OK
	HH			4.2.3 / a) Describe methods to identify hazards / b) ... events / c) Methods/tools for risk computation (can be incomplete/tentative at the current stage) / d) Define process		OK
	HH			4.3 Summary of Proof of Concept / (refer to the plan from 4.2)		OK
	HH			5. openETCS Safety Case / This section is a plan for producing the Safety Case. State this. / First paragraph: The SC has to present the main line of argumentation and refer to evidence. / Proposal: Define the outcome. (A partly generic SC which can be instantiated in a real development, move this from 5.1)		OK
	HH			5.1 Structure / Proposal: Present what you intend for the structure (basic assumptions, safety argumentation and reference to evidence)		OK
	HH			5.1.2 / Which "basic process"?	term replaced	OK
	HH			5.1.3 / The evidence will come from verification steps, tracing, and perhaps validation. "overall safety principles" can at most be observed during development but hardly validated	content adopted	OK
	HH			5.2 / Read the first paragraph and ask yourself whether you would now use a similar wording if you had to write it again :). (IMHO it is not easy to understand)	restructured pharagrap	OK
	HH			5.2.1 / "modeled documentation of the EN 50128 ..." ???Details	changed sentence to be more concrete	OK
	MPD			Current version of the document is a good introduction to the attendee to cover safety issue according the current state of the project.		Ok
	MPD			§ 3 Why tool qualification is out of the scope of the project ? an output is plan in WP7 dealing with this subject. And tool qualification has a strong link with design and VnV chosen methods.	Yes, tool qualification is not out of scope overall. I changed the text in the way that openETCS project will not provide a completely qualified tool chain, but one that may be qualified in the future.	Ok
	MPD			§ 3.2.3 : I think that goal of verification is not only to verify system safety requirements but also to verified selected methods are well applied according to some methodological requirements (links to the quality plan). for example no dead code, naming convention,... Some example of such static verifications are done in D4.2.2 part one.	It is correct. I added this point to the chapter	OK
	MPD			§ 4.2 : The safety requirements issued from this analysis have been formally specified and proved on an Event-B model : https://github.com/openETCS/validation/blob/master/VnVUserStories/VnVUserStorySysterel/04-Results/d-EventB-VnV/EventB-Rodin-VnV.pdf	has been included in the report as a short document reference	OK
	MPD			§5 Is method or means proposed in openETCS to improve the management of documentation ?	yes, added in introduction	Ok
	MPD			§ 5.1 : According to EN50129, the following part is missing in the description of the structure of the safety case : "Description of the system : precise the scope of the system covered by the safety case". This is really important to define the scope of the risk and hazard analysis.		OK
	MPD			§ 5.2 : For future iteration of document, link to concrete example of the model-based Argumentation will be useful.		Open
	MPD			For future iteration of the document, and maybe linked with the Safety plan: Impact of scrum process and short iterations is discussed in regards of hazard and risk analysis (in §4), however how this specific process si managed in regards of documentation, verification and validation ?		Open
	MPD		Minor comments:	§1.2 "and th safety" -> "and the safety"		OK
	MPD		Minor comments:	§1.5.2 "These can be assess for the software b independent measures" : not clear	Sentence reformulated to clearify the meaning	OK
	MPD		Minor comments:	§ 1.5.3 "These depenences" -> These dependences"	corrected	OK
	MPD		Minor comments:	§ 2 "and detail" -> "and detailed"	Sentence has been rephrased	OK
	MPD		Minor comments:	§ 2 "This specifically reference..." : the phrase is not clear	Sentence has been rephrased	OK
	MPD		Minor comments:	§ 3 "OpenETCS tools chain" -> OpenETCS tool chain"	corrected	OK
	MPD		Minor comments:	§ 3 "used to formalizes" -> "used to formalize"	corrected	OK
	MPD		Minor comments:	§ 3 "focus focus" -> "focus"	corrected	OK
	MPD		Minor comments:	§ 3 introduction is not clear and not finished	corrected	ok
	MPD		Minor comments:	§ 3.1 "principals" -> "principles" / "in a detail formal" -> "in a detailed formal" / "5 main distinguishable phase" -> "5 main distinguishable phases" / "performed iterative" -> "performed iteratively"	corrected	OK
	MPD		Minor comments:	§ 3.2.2 "during the during the" -> "during the"	corrected	OK
	MPD		Minor comments:	§ 3.2.3 "The v&v plan do specify" -> "The v& v plan shall specify"	corrected	OK
	MPD		Minor comments:	§ 4 "have to been determined" -> "have to be determined" / "the principal software" -> "the principle software"	corrected	OK
	MPD		Minor comments:	§ 5.1 "that the can directly be used..." : not clear	changed sentence	OK
	MPD		Minor comments:	§ 5.1.3 "principals" -> "principles" (several times in the document) / "the safety case clear has to show" : not clear	corrected and sentence changed	OK
	MPD		Minor comments:	§ 5.2 "is address" -> "is addressed" / "safety case present" -> "safety case presents"	corrected	OK
	AM	2	Minor correction	Please Correct: / "So far this version of D4.2.3 covers an introduction to the openETCS develpement process, the high-level safety principals defined by the ETCS system documentaion and the basic plans for hazard and risk analysis and th (the)…."	corrected	OK
	AM	2	Minor correction	Please Correct: / "These (This) section shall presenst and clarify the underlying of safety it (is) in standards..."	corrected	OK
	AM	2	Minor correction	Please Correct: / "The basic open ETCS software (development)…."	corrected	OK
	AM	3	Minor correction	Please Correct: / "… the given requirements always present the objective against which the system hast be measured (with)(End of sentence?)"	corrected by using up to	OK
	AM	4	Minor correction	Please Correct: / "These can be (assessed) …."	corrected	OK
	AM	4	Minor correction	Please Correct: / "Safety in the railway development as defined in EN 50126 is (in)..." / "These (dependancies) …"	in corrected, / Dependancies (AE) or dependencies (BE)	OK
	AM	5 and 6	Minor correction	Please Correct: / "The risk control process as it is presented in figure 4 is then performed to ensure that the safety integrity levels (are reached)…." / "Since Software itself does not (fail)…" / " (These Tasks) are related …."	Corrected / Corrected / Corrected	OK
	AM	8	Minor correction	Please Correct: / "Both parts have thier own develpment Process, but the focus (focus) …." / End of the passage needs to be completed!	Corrected / Completed	OK
	AM	9	Minor correction	Table 1 on P4 : Code Generation Phase "This C Code is than (then) compiled…"	Corrected	OK
	AM					OK
	AM	9	Minor correction	"Although the phase represent differnt working steps in the life cycle according to EN 50128 the agile development process applied in openETCS induces that the phases are performed (iteratively)….."	correted	OK
	AM	9	Minor correction	"As (shown)…."	corrected	OK
	AM	10	Minor correction	"Thereby, potentiall hazards resulting from the software funcionaltiy and ist design have to be identified and their risk has to be (assesd) in the system concept. To control the risk respective measures have to be taken, which (can) be realized…."	sentence change completely	OK
	AM	10	Minor correction	"This has to be done for all abstracion levels (during the)..."	part delited	OK
	AM	10	Minor correction	"Therefor, it has to be ensured specifcally that the Software in (its) System..."	corrected	OK
	AM	12	Minor correction	"…, the specific Safety requirements for the on-board unit have to (be) determined …"	corrected	OK
	AM	12	Minor correction	"In relation to SUBSET-091 further documents should be (taken) …."	corrected	OK
	AM	13	Minor correction	"Cased on the principal Software architecture the risk can be (assessed)…"	corrected	OK
	AM	15	Minor correction	"As the proof of concept has (clearly) shown ..."	corrected	OK
	AM	16	Minor correction	"In general the safety case has to present to the assessing authority that the development has (been) done according….."	corrected	OK
	AM	16	Minor correction	"…, it is highly important to collect all relevant documents in a way, that (they)....."	sentence changed, corrected	OK
	AM	17	Minor correction	"For all (evidences to be) produced during the openETCS process the safety case (clearly)….."	sentence changed, corrected	OK
	AM	17	Minor correction	"The argumentation demonstrates how each requirement will be (addressed)…." / "In addition…. the right information from the diverse data base structure of the (openETCS)…"	Corrected / Corrected	OK
	AM	17 and 18	Minor correction	"An ideal support for the automatic evolution of the safety case would be (provided)…" / "The effort needed to connect this tool to eclipse and github during the openETCS project was (set) (as) to high."	Corrected / Replaced by „seen as“	OK

## Main Issues
Main/Open Issues

#	Title	Description	Proposal	Status
1	Reference to central Development Process description	OpenETCS development process shall be presented in one central place for all other documents to reference	Activities to combine existing descriptions in Quality Assurance Plan (respectively a seperated Development Plan)	started (by Hardi Hunger)
2	Safety Plan with clear document structure needed	Clearly a first real safety case structure is needed referencing the life cycle phase for the project and showing the planed artifacts as well as the responsable parties.	This document will be started by Jan Welte by using the methodology proposed in this document. The reference life cycle will be the starting point for this document.	to be started in May (by Jan Welte
3	Details for model-based argumentation	Link to concrete example of the model-based Argumentation has to be presented	Will be done in the future work to present a more precise and detailed plan	to be started in May (by Jan Welte
4	Management process for H and R analysis in SCRUM	Concrete scrum management process for the hazard and risk analysis has to be established. This also requires a detailed coordination with documentation and V&V process.	Has to be discussed in WP 4 as we do not has the resources for many iterations.	Addressed during Second Iteration